Why Estimate Size?
Why Estimate Size? - 1
To make better plans
  - to better size the job
  - to estimate how long it will take
If we have a good size estimate we can calculate estimated hours:
- Est. Size divide by Historical LOC/hr = Est. Hrs
- 60 / 20 = 3

---
Why Estimate Size? 2
Why Estimate Size? - 2
- To assist in tracking progress
  - can judge when job scope changes
  - can better measure the work
  - If you're 2 hrs into the job and have 50 lines complete you're ahead of schedule.
- Value in this course
  - learn estimating methods
  - build estimating skills

---
Current Practice
Current Practice
- Software size estimating experience
  - 100% + errors are normal
  - few developers make estimates
  - fewer still use orderly methods

---
Estimating Accuracy
Estimating Accuracy

---
Size Estimating Principles - 1
Size Estimating Principles - 1
Estimating is an uncertain process.
  - no one knows how big the product will be
  - the earlier the estimate, the less is known
  - estimates can be biased by business and other pressures
- Estimating is an intuitive learning process.
  - ability improves with experience
  - some people will be better at estimating than others

---
Size Estimating Principles - 2
Size Estimating Principles - 2
Estimating is a skill.
  - improvement will be gradual
  - you may never get very good
- The objective, however, is to get consistent.
  - you will then understand the variability of your estimates
  - you seek an even balance between under and over estimates

---
Size Estimating Principles - 3
Size Estimating Principles - 3
The principal advantages of using a defined estimating method are
  - you have known practices that you can work to improve
  - it provides a framework for gathering estimating data
  - by using consistent methods and historical data, your estimates will get more consistent

---
Common Estimating Approaches
Common Estimating Approaches
- Function points - not measurable from code
- Delphi - panel of experts
- Fuzzy logic, Standard components - use historical data
- Humphrey’s method: Proxy based, also uses historical data

---
Estimation Approaches
Estimation Approaches in 301
- Wag: “Wild *ssed Guess”
- Informal Estimate: qualitative, without consulting historical data.
- Formal Estimate: quantitative, may consult historical data.

---
Informal Estimation
Informal Estimation
301 will mostly rely on Informal Estimate
  - Most developers do NO estimating so even qualitative will be a quantum leap
  - Simple feedback is enough to prompt significant learning (e.g. phone book estimating)
  - Informal methods may be good enough, so try them first. Can always advance to formal methods later.
  - Formal methods require historical data and we don’t have any.
  - Our process isn't stable enough.
  - Until quality is managed time is unpredictable.

---
Informal Estimating Procedure
Informal Estimating Procedure
- Study the requirements
- Sketch out a crude design
- Decompose the design into “estimatable” chunks.
- Make a size estimate for each chunk, using a combination of:
  - visualization
  - recollection of similar chunks that you’ve previously written
  - intuition
Add the sizes of the individual chunks to get a total.

---
Informal Estimating Example
Informal Estimating Example
- Module Description	Estimated Size
- Get File Name	8
- Get Operating Mode	8
- Open File	10
- Display Numbers	10
- Obtain Numbers	12
- Total	48

---
Estimating Worksheet
Estimating Worksheet
- 1. Conceptual Design (sketch your design here)
- 2. Module Estimates
Module	Estimated Size
Total

---
PSP1 Estimating
PSP 1 Estimating
- In PSP 1 we'll use size estimate to estimate total time and time in phase.
- Calculate estimated hours:
- Est. Size divide by Historical LOC/hr = Est. Hrs
- 60 / 20 = 3
- Est. mins * Historical % time in design =
- 180 * 10% = 18